## Checklist
Sample Client Review Process Checklist
Step 1 - Discovery
Action Item |  | Within | Date Due | Date Done | Done By | Forms | Notes
1 | Contact new client and schedule all New Client Meetings (Discovery, Date Review, Plan Review, Implementation, 45-day Review) | 3 days of prospect decision |  |  | Admin | Procedure - New Client Meeting Invites
2 | Update electronic / physical folders for clients and add to relevant databases / distribution lists | 1 wk post decision |  |  | Admin | Procedure - New Client Files
3 | Send FP Discovery Packet | 3 days of prospect decision |  |  | Jr Advisor | Discovery Packet Discovery Questionnaire Client Affinity Form COI Request
4 |  | 1 wk of delivery |  |  | Client
5 | Meet to review Discovery Materials | 3 days following receipt |  |  | Team
6 | Prepare meeting materials | 1.5 wks prior to meeting |  |  | Team as assigned | Discovery Meeting Agenda Related materials per topic
7 | Review / finalize meeting materials | 1 wk prior to meeting |  |  | Advisor
8 | Send meeting reminder | 1 wk prior to meeting |  |  | Admin | Meeting Reminder
9 | Prepare final meeting materials | 3 days prior to meeting |  |  | Jr Advisor
10 | Hold Discovery Meeting | As scheduled |  |  | Advisor
11 | Draft meeting follow up and get approval from advisor | 24 hours of meeting |  |  | Advisor / Jr Advisor | Discovery Meeting Follow Up
12 | Send meeting follow up | 24 hours of meeting |  |  | Advisor
13 | Coordinate with COIs regarding identified items | As appropriate |  |  | Advisor
14
15
Step 2 - Plan / Design
Action Item |  | Within | Date Due | Date Done | Done By | Forms | Notes
1 | Prepare initial draft of plan | 2 wks of meeting |  |  | Jr Advisor | Procedure - Plan Preparation
2 | Review initial draft of plan and draft recommendations | 1 wk of receipt |  |  | Advisor
3 | Hold data review meeting | 1 wk of plan review |  |  | Advisor / Jr Advisor | Data Review Meeting Agenda
4 | Draft meeting follow up and get approval from advisor | 24 hours of meeting |  |  | Jr Advisor | Data Review Meeting Follow Up
5 | Send meeting follow up | 24 hours of meeting |  |  | Jr Advisor
6 | Revise plan per advisor recommendations | 2 wks prior to meeting |  |  | Jr Advisor
7 | Finalize plan recommendations and instruct team on development of solutions | 1 wk prior to meeting |  |  | Advisor
9 | Send meeting reminder | 1 wk prior to meeting |  |  | Admin | Meeting Reminder
8 | Prepare final meeting materials | 3 days prior to meeting |  |  | Jr Advisor | Plan Review Meeting Agenda Plan of Action Related materials per topic
10 | Hold Plan Review Meeting | As scheduled |  |  | Advisor / Jr Advisor
11 | Draft meeting follow up and get approval from advisor | 24 hours of meeting |  |  | Jr Advisor | Plan Review Meeting Follow Up
12 | Send meeting follow up | 24 hours of meeting |  |  | Advisor
13 | Client decision follow up process | Weekly until decision or 3 follow ups |  |  | Advisor | 3-Step Follow Up Process
14 | Client makes implementation decision | 2 wks of meeting |  |  | Client
15
Step 3a - Implement (Account Establishment)
Action Item |  | Within | Date Due | Date Done | Done By | Forms | Notes
1 | Update CRM with new client information - change client from "Prospect" to "Client" | 2 days post decision |  |  | Admin
2 | Prepare and send New Client Welcome Packet | 2 days post decision |  |  | Admin | Welcome Packet Welcome Letter Meet the Team Service Model & Fees Process Overview
3 | Schedule Implementation Meeting | 2 days post decision |  |  | Admin
4 | Update electronic / physical folders for clients and add to relevant databases / distribution lists | 1 wk post decision |  |  | Admin | Procedure - New Client Files
5 | Prepare all account paperwork and product applications for all applicable products and place in client file for Advisor review | 2 wks prior to meeting |  |  | Admin Advisor | Procedure - New Account Setup Related materials per topic | Follow up on any pending items
6 | Draft meeting agenda | 2 wks prior to meeting |  |  | Jr Advisor | Implementation Meeting Agenda
8 | Prepare meeting materials | 1 wk prior to meeting |  |  | Team as assigned | Related materials per topic
7 | Send meeting reminder as well as any account paperwork to bring to meeting or complete in advance of meeting | 1 wk prior to meeting |  |  | Admin | Meeting Reminder Related materials per topic
9 | Review / finalize meeting materials | 3 days prior to mtg |  |  | Advisor
10 | Prepare final meeting materials | 2 days prior to mtg |  |  | Jr Advisor | Related materials per topic
11 | Hold Implementation Meeting and edit all applicable paperwork during meeting | Day scheduled |  |  | Advisor / Jr Advisor
12 | Draft meeting follow up and get approval from advisor | 24 hours of meeting |  |  | Jr Advisor | Implementation Mtg Follow Up
13 | Send meeting follow up | 24 hours of meeting |  |  | Advisor
Step 3b - Implement (Transition to Client Review Process)
Action Item |  | Within | Date Due | Date Done | Done By | Forms | Notes
1 | Initiate appropriate accounts for all products discussed during Implementation Meeting | 1 wk post meeting |  |  | Team as assigned | Procedure - New Account Setup Related materials per topic
2 | Follow-up on initiated accounts until established | 2-4 wks post review |  |  | Jr Advisor | Weekly Status E-mail | Follow up weekly
3 | Notify team that client paperwork is complete and accounts have been established | Upon completion |  |  | Jr Advisor
4 | Assign service model tier based on discussion and fit | Upon completion of account set up |  |  | Advisor | Service Model
5 | Update CRM with new client information - assign appropriate service model tier | Up completion of account set up |  |  | Jr Advisor | Procedure - Service Model Set Up
6 | Set reminders to schedule recurring actions based on service model | Up completion of account set up |  |  | Jr Advisor | Procedure - Service Model Set Up
7 | Prepare meeting materials | 1.5 wks prior to meeting |  |  | Team as assigned | 45 Day Review Meeting Agenda Related materials per topic
8 | Review / finalize meeting materials | 1 wk prior to meeting |  |  | Advisor
9 | Prepare final meeting materials | 3 days prior to meeting |  |  | Jr Advisor | Related materials per topic
10 | Conduct 45 day review meeting | As scheduled |  |  | Advisor / Jr Advisor
11 | Draft meeting follow up | 24 hours of meeting |  |  | Jr Advisor | Meeting Follow Up
12 | Send meeting follow up | 24 hours of meeting |  |  | Advisor
13 | Schedule Client Reviews | 1 wk of meeting |  |  | Admin | Procedure - Client Review Scheduling
14
Exhibit 30

## Disclosure
IMPORTANT INFORMATION This is for informational purposes only, is not a solicitation, and should not be considered investment or tax advice. This information has been drawn from sources believed to be reliable, but its accuracy is not guaranteed, and is subject to change. Investing involves risk, including the possible loss of principal. Past performance does not guarantee future results. AssetMark, Inc. is an investment adviser registered with the Securities and Exchange Commission. AssetMark and third-party strategists and service providers are separate and unaffiliated companies. ©2019 AssetMark, Inc. All rights reserved. M19-67795 ¦ 11/2019 ¦ EXP 11/30/2020 For financial advisor use only.